## Agile Template
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to ExamGuard project and requirement analysis | MUST HAVE | No Dependency | Team | 3- Completed
S1 | S1 | US-002 | Workflow creation and project goal document | MUST HAVE | US-001 | Team | 3- Completed
S1 | S1 | US-003 | Research and preparation of online examination use cases | SHOULD HAVE | US-002 | Team | 3- Completed
S2 | S2 | US-004 | Candidate registration and login functionality | MUST HAVE | US-003 | Team | 3- Completed
S2 | S2 | US-005 | Online examination interface with questions and answer options | MUST HAVE | US-004 | Team | 3- Completed
S2 | S2 | US-006 | Examination timer and question navigation | MUST HAVE | US-005 | Team | 3- Completed
S3 | S3 | US-007 | Webcam access using WebRTC getUserMedia | MUST HAVE | US-005 | Team | 3- Completed
S3 | S3 | US-008 | Live face monitoring using MediaPipe Face Mesh | MUST HAVE | US-007 | Team | 3- Completed
S3 | S3 | US-009 | No-face and multiple-person detection | MUST HAVE | US-008 | Team | 3- Completed
S4 | S4 | US-010 | Looking left, right, up and down detection | MUST HAVE | US-008 | Team | 3- Completed
S4 | S4 | US-011 | Warning counter and examination termination | MUST HAVE | US-010 | Team | 3- Completed
S4 | S4 | US-012 | Browser tab-switch and window monitoring | MUST HAVE | US-011 | Team | 3- Completed
S5 | S5 | US-013 | Automatic examination submission and result calculation | MUST HAVE | US-006 | Team | 3- Completed
S5 | S5 | US-014 | Store examination and proctoring events in SQLite | MUST HAVE | US-011 | Team | 3- Completed
S6 | S6 | US-015 | Testing of ExamGuard examination and monitoring features | MUST HAVE | US-014 | Team | 3- Completed
S6 | S6 | US-016 | Project documentation and deployment preparation | SHOULD HAVE | US-015 | Team | 2- In Progress